## Sheet1
Task Name | Start | End | Duration (days)
Build Experimental Set-up and Calculate Estimated Results | 2017-04-13 | 2017-04-18 | 5
Build Airfoils | 2017-04-16 | 2017-04-18 | 2
Conduct Experiment | 2017-04-18 | 2017-04-19 | 1
Analyze Experimental Data and Compare to Calculated Data | 2017-04-19 | 2017-04-24 | 5
Write Final Report | 2017-04-24 | 2017-05-07 | 13
Prepare to Present | 2017-04-30 | 2017-05-02 | 2
In Class Presentation | 2017-05-02 | 2017-05-03 | 1
In Lab Presentation | 2017-05-03 | 2017-05-04 | 1
Incorporate Feedback into Report | 2017-05-04 | 2017-05-07 | 3
Turn in Report | 2017-05-07 | 2017-05-08 | 1